## Sheet1
TECHNICAL COMMITTEE WORKPLAN - 2018
Strategic Responsibility | Deliverable | Action | Priority | Personnel | Status
[5 empty] | JAN | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC
COACH EDUCATION | Advice on strategies and actions to build the capability of coaches | Assist in building continuous learning framework for coaches; assist with formation of workshop/course yearly plan |  | GNZ Education Manager; TC Chair; TC Coacing Advisor
| Technical advice on amendments, updates, innovations and ideas within required timeframes | Improve and seek input into manuals |  | TC Coaching Advisor
|  | Improve and seek input into resources |  | TC Coaching Advisor
|  | Improve and seek input into courses |  | TC Coaching Advisor
|  | Improve and seek input into training forums |  | TC Coaching Advisor
| Update and/or develop coaching resources - online and physical manuals | Review content - videos and manuals |  | TC Coaching Advisor
|  | Undertake and collect material required for coaching resources (videos and written material) - as required post review |  | TC Coaching Advisor
|  | Finalise material with Education Manager |  | GNZ Education Manager; TC Coaching Advisor
|  | Assist with the publication and communication of resources |  | GNZ Education Manager; TC Coaching Advisor
| Develop and implement coach education within National Education Framework | Contribute to the annual education & training programme by ??? |  | GNZ Education Manager; TC Coaching Advisor
| Assist in the establishment of a mentoring programme; Develop and maintain relationships with coaches | Improve and seek input into mentoring programme |  | TC Coaching Advisor
| Assist in the establishment of up skilling standards within GSNZ education strategy | Review and update standards |  | GNZ Education Manager; TC Chair; TC Coaching Advisor
| Establish/review a development and succession plan |  |  | GNZ Education Manager; TC Chair; TC Education Advisor
| Assess new and existing coaches for Recognition of Prior Learning and Master Coach | Improve and seek input into standards for Master coach qualifications; assess recongintion of prior learning applications |  | TC Coaching Advisor
| Remain up to date with current sport coaching practices nationally & internationally | Attend national squad training as required; attend personal devleopment opportunities as required |  | TC Coaching Advisor
JUDGE EDUCATION | Technical advice on improvements & developments within National Education Framework (to required timeframes) | Improve and seek input into Manual (handbook/domestic manual?) annually by November each year |  | TC Judging Advisor
|  | Improve and seek input into judging course resources |  | TC Judging Advisor
|  | Improve and seek input into courses |  | TC Judging Advisor
|  | Improve and seek input into training forums |  | TC Judging Advisor
| Ensure the Discipline is in alignment with the FIG Code of Points by | Provide advice on Regulations |  | TC Judging Advisor
|  | Lead technical rules for judges (code specific) |  | TC Judging Advisor
|  | Advise of international amendments and innovations including variations |  | GNZ Education Manager; TC Judging Advisor
| National judging framework for each code | Improve and seek input into judge education |  | GNZ Education Manager; TC Judging Advisor
| Verify judging panels for competitions – national, regional and sanctioned | Confirmed panels provided two weeks prior to event, with nomination of Control Judge for Nationals by end of February |  | GNZ Education Manager; TC Judging Advisor
| Verify logbooks and results from judging courses within required timeframes | All Log books and results verified within 5 days of submission |  | TC Judging Advisor; GNZ Education Manager;
| Assessing, approving/declining athlete re-grades and dispensations throughout the year processing in a timely manner | All applications processed within 5 working days |  | TC JudgingAdvisor
PERFORMANCE | Identify and approve a programme of events and tours for competitive participation each calendar year (where possible plan beyond 12 months setting event programmes to prioritise recruitment and retention of athletes) | Increase the number of athletes attending competition events by ?% |  | GNZ Performance Pathways Manager; TC Chair; TC Performance Advisor
| Succession plan for coaches & judges - required number of tours to be attended to retain qualifications (judges) and development (coaches) | Increase the number of coaches and judges attendance by ?% |  | TC Chair; TC Performance Advisor
| Tours Logistics - confirmed tours on the International Events Calendar | Qualification criteria set (age-level and international streams) |  | TC Chair; TC Performance Advisor
Call for Intention to Travel (ITT)
ITT (participation and performance events) – nominate team based on ITT’s; provide rationale for performance event nominations (selection for performance event decided by GNZ)
|  | Set management fee if applicable |  | TC Performance Advisor
|  | Select chaperones and team managers |  | TC Performance Advisor
|  | Set travel dates for selected athletes where required |  | TC Chair; TC Performance Advisor
|  | Assessing athlete applications for extenuating circumstances and/or participation on tours |  | TC Performance Advisor
| Where required, liaise and assist Gymnastics NZ National Coaches for the development of a high performance programmes | ???? |  | GNZ Performance Pathways Manager; TC Chair; TC Performance Advisor
COMPETITIVE PATHWAYS | Qualifying competitions:
| Logistics - GNZ confirmed annual qualifying competitions | Determine the technical rules, including any variations to the FIG rules by end of November |  | TC Chair; TC Competitive Advisor
|  | Establish criteria and application process for hosting qualifying competitions by end of October |  | Events Manager; TC Competitive Advisor
|  | Reviewing applications and selecting clubs to host qualifying competitions by end of November |  | Events Manager; TC Competitive Advisor
Ensure judging panels meet the minimum requirements - remove, keep under judging advisor
National Championships:
| Logistics - pre Event tasks/responsibilities that deliver the National Championships to a high standard | Oversee provision of equipment and ensure meets appropriate standard - year round |  | TC Competitive Advisor
|  | Control judge to nominate judges to be invited in March, create judging panels and ensure equipment is of an appropriate standard by event |  | Events Manager, TC Competitive Advisor
|  | Review rules and regulations annually ,e.g. dispensations, substitutions, withdrawals etc., by end of June |  | TC Chair; TC Competitive Advisor
|  | Make recommendations in response to applications for dispensation within 5 days of the entry closing date |  | TC Competitive Advisor
|  | Review work plan - 1st draft due end of June; final draft, due 3 weeks post en try closing date |  | TC Competitive Advisor
|  | Create competition timetable - draft due end of May, final due 2 weeks post entry closing date |  | Events Manager, TC Competitive Advisor
|  | Set qualification by end of Feb and proficiency scores by end of July |  | TC Chair; TC Competitive Advisor
|  | Run TC forum at event |  | TC Chair; TC Competitive Advisor
|  | Where required/instructed, create Run Lists, Warm Up Schedules and complete Draw - due 2 weeks post entry closing date |  | TC Competitive Advisor
| Assist Events Manager with feasibility studies for hosting international events | Bid to host a FIG sanctioned event successfully submitted |  | Events Manager; TC Chair; TC Competitive Advisor